## Sheet1
| Start of Week | 2013-08-26 | 2013-09-02 | 2013-09-09 | 2013-09-16 | 2013-09-23 | 2013-09-30 | 2013-10-07 | 2013-10-14 | 2013-10-21 | 2013-10-28 | 2013-11-04 | 2013-11-11 | 2013-11-18 | 2013-11-25 | 2013-12-02 | 2013-12-09 | 2013-12-16 | 2013-12-23 | 2013-12-30 | 2014-01-06 | 2014-01-13 | 2014-01-20 | 2014-01-27 | 2014-02-03 | 2014-02-10 | 2014-02-17 | 2014-02-24 | 2014-03-03 | 2014-03-10 | 2014-03-17 | 2014-03-24 | 2014-03-31 | 2014-04-07 | 2014-04-14 | 2014-04-21 | 2014-04-28 | 2014-05-05
| End of Week | 2013-08-30 | 2013-09-06 | 2013-09-13 | 2013-09-20 | 2013-09-27 | 2013-10-04 | 2013-10-11 | 2013-10-18 | 2013-10-25 | 2013-11-01 | 2013-11-08 | 2013-11-15 | 2013-11-22 | 2013-11-29 | 2013-12-06 | 2013-12-13 | 2013-12-20 | 2013-12-27 | 2014-01-03 | 2014-01-10 | 2014-01-17 | 2014-01-24 | 2014-01-31 | 2014-02-07 | 2014-02-14 | 2014-02-21 | 2014-02-28 | 2014-03-07 | 2014-03-14 | 2014-03-21 | 2014-03-28 | 2014-04-04 | 2014-04-11 | 2014-04-18 | 2014-04-25 | 2014-05-02 | 2014-05-09
| Milestones | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37
| Deliverable | Flowchart & ERD | Flowchart & ERD | System Requirement Study and Design Document |  |  |  | Prototype I | Prototype I | Development I | Development I | Prototype I | Development I | Prototype I | Development II | Development II | Prototype II | Development III | Development III | Prototype III | Training | UAT | UAT | Data Migration | Live Running System | Post-live fine-tune & support | Post-live fine-tune & support | Post-live fine-tune & support | Post-live fine-tune & support | Warranty | Warranty | Warranty | Warranty | Warranty | Warranty | Warranty | Warranty | Warranty
1 | Project Initiation | 2013-08-30: Kick-off Meeting
2 | System Analysis & Design | 2013-09-13: System Analysis & Design
3 | Prototype and Demonstration | 2013-10-11: Program Publication & Application; 2013-11-29: Interviews & Nominations Management; 2013-12-20: Appointment Management & Student Profile
4 | Training & UAT | 2014-01-10: Training & UAT
5 | Data Migration & Live Run Preparation | 2014-01-31: Data Migration; 2014-02-07: Live Run
6 | Payment Schedule | 2013-10-11: *40%; 2014-01-10: *30%; 2014-02-07: *30%